## Roadmap
Approved by Mongolia EITI National Council Meeting
dated December 20th of 2016
Updated by Mongolia EITI National Council Meeting
dated December 21nd of 2017
ROADMAP 2016-2020 FOR THE DISCLOSURE OF INFORMATION BENEFICIAL OWNERS WITHIN THE EXTRACTIVE INDUSTRIES TRANSPARENCY INITIATIVE STANDARD
Goal: To increase general public oversight and owners accountability through disclosing Beneficial Owners of corporate entity(ies) that bid for, operate or invest in extractive sector
Objectives | Planned activities | Outcome | Product | Responsible party | Timeframe | Budget |  | Status
[6 empty] | Amount (thous.mnt) | Source
Objective 1: To link BO disclosure with National Reform Priorities | 1.1 Organize meeting with Open Government Partnership | Joint activities will be determined | Joint work plan | Senior Advisor to the Prime minister, MoMHI | Jan-Mar 2017 | 500 | WB | Completed
| 1.2 Organize Round Table meeting for Parliamentarians and Government organizations | Parliement members will be aware of BO issues | Meeting minute | EITIIS | Mar-Apr, 2018 | 10,000 euro | EBRD
| 1.3 Organize Press Release together with OGP and EITI National Council to jointly express their position on BO disclosure issues into public | Interested stakeholders will came in common understanding | Joint statement | OGP, EITINC, CGNC | Apr 2018 | 100 | WB
Objective 2: To identify institutional framework for BO disclosure | 2.1 Organize consultation seminar within government organizations which registers BO information and reach common understanding, find out recommendations /60 people, 1 time/ | Which government organization will register and maintain BO information, what legal documents will need to amend will be determined. | Recommendation | Secretariat of Prime Minister, EITIMS | Jun 2017 | 4000 | WB | Completed
| 2.2 Ensure better coordination between EITI and Legal Working Group established at MoMHI | Improved coordination and communication | Meeting minute | MoMHI | Jan-Sep 2018 | 1000 | WB | In process
| 2.3 Draft the BO amendments to the related laws, submit the draft law | Law amendments will be drafted | Draft law | MoMHI, EITIIS, Consultancy Firm | Jan-Sep 2018 | 50,000 euro | EBRD
Objective 3: To identify "Beneficial ownership" terminology, definition, disclosure threshold, level of detail through broader consultation with stakeholders | 3.1. Organize consultation seminar on "Terminology" /40 persons, 1 time/ | Exact definition will be determined | Minutes | OSF, EITIMS | Dec 2016 | 0 | OSF | Completed
| 3.2 Create data base on other countries experience on BO disclosure | Data base will be created for experience sharing | Data base | EITIMS | Jan-Dec 2017 | Operating cost | WB | Completed
| 3.3 Finalize preliminary study on Mongolian legal environment and dessaminate stakeholders | Fundamental document will be finalized and stakeholders will got general background | Survey report | OSF | Feb 2017 | Estimated budget | OSF | Completed
| 3.4 Consultation workshop within company representatives /60 people/ | Comments will be wrapped up | Minutes of consultation | EITIMS | Feb, Apr 2017 | 4597.7 | WB | Completed
| 3.5 Consultation workshop within government organizations /40 people/ | Comments will be wrapped up | Minutes of consultation | MoMHI, EITIMS | Feb, Jun 2017 | 232.9 | WB | Completed
| 3.6 Consultation workshop within civil society organizations /60 people/ | Comments will be wrapped up | Minutes of consultation | PWYP, EITIMS, LPRH | Nov 2017 | Estimated budget | OSF, LPRH | Completed
| 3.7 Joint consultation within stakeholders /150 people/ | Stakeholders will came in consensus | Recommendation | EITI MSWG | Mar 2017 | 0 | WB | Postponed
| 3.8 Discuss and agree on "terminology, definition, threshold, level of detail of BO disclosure" by EITI MSWG, NC meeting | Stakeholders consensus will be guarenteed and documented officially | Minutes of Meeting and Decision | EITIMS | Nov 2017 | 0 | WB | Completed
Objective 4: If Political Exposed Person is beneficial owner of extractive industry, then ensure complete disclosure of his/her information. | 4.1 Precisely identify "Politically Exposed Beneficial Owner" definition | PEBOs will be reported completely | Recommendation | IAAC, EITI MSWG | Jan-Jun 2018 | 500 | WB
| 4.2 Amend related laws and update reporting template | Reporting mechanism shall be ensured | Amendment draft to related laws |  | Mar-Sep 2018 | 500 | WB
Objective 5: Organize promotional activities for companies to disclose BOs by themselves through increasing public awareness | 5.1 Training and consultation workshop for executives and senior legal officers of companies /25 people, 3 series/ | Acceptance of the requirement and mutual understanding will be increased | Minutes | EITIIS | May 2018 | 15,000 euro | EBRD
| 5.2 Training for trainers comprises from civil society and NGOs /20 people, 3 series/ | Public debate will be activated by trained trainers | Public debate | EITIIS | Mar-May 2018 | 60,000 euro | EBRD
| 5.3 Establish investigative journalists network and train them /10 journalists, 3 series/ | Targeted TV programmes, articles, interviews will be broadcasted | TV products and messages for social media | EITIIS | Mar-Dec 2017
| 5.4 Conduct survey on company incentives mechanism for those dislosed BO information on their own | Possible incentives' mechanisms will be conducted | Survey report | BO Sub-working group | Jan-Feb 2018 | 5000 | WB
| 5.5 TV live discussion /2 times/ | Public awareness and engagement will be increased | TV live discussion | EITINC | Nov-Dec, 2017 | 0 | WB | Completed
Objective 6: Collect the BO information and assure the accuracy of data | 6.1 Synchronize the registration system of government agencies which register and maintain BO information and improve information sharing within those GOs | Information collecting and sharing system will be synchronized | Incorporated system of government organizations | IAAC, CGNC, EITIWG, Consultancy Firm | Jan-Jul 2018 | 70,000 euro | EBRD
| 6.2 Organize training for GO's related with BO registration process | Capacity of GO's will be strenthened | Training report |  | Aug-Oct 2018
| 6.3 EITI MSG stakeholders agree on data assuring methodology | Assuring methodology will be identified | National Council meeting minutes | EITIMS | Oct 2018 | 500 | WB
| 6.4 Pilot information gathering process of beneficial owners | System will be tested and any difficulties will be evaluated | Report | Government organizations | Jun 2018-Mar 2019 | 1000 | WB
| 6.5 Pilot assuring process of information gathered | Assuring methodology will be evaluated | Report | CSOs, IAAC, MNAO | Mar-Jun 2018 | Incorporated CSO training budget | EBRD
| 6.6 Amend related regulations and templates | Related amendments will be done | Updated regulation and template | EITINC | Jul - Oct 2018 | 300 | WB
| 6.7 Advertise new regulation and template into public | Key target group will be informed | Promotional materials | EITINC | Oct-Dec 2018 | 3000 | WB
| 6.8 Collect and disclose BO information through MEITI 2018 Report | Data will be collected | Data base incorporated into EITI Report 2018 | EITI NC, MSWG, Secretariat, related Gos | Jan-Jul 2019 | 5000 | WB
| 6.9 Link General Taxation Department system with OECD system | Information about Offshore account transitions will be available | System | EITI NC, GDTaxation, CGNC | Jan-Dec 2018 | System cost | Donors
Objective 7: Ensure BO information is disclosed publicly accessible | 7.1 Link to other e-Reporting system and disclose the BO information into public | BO information will be disclosed into public | Electronic data system | IAAC, CGNC, EITI, Media organizations | Jan-Jul 2019 | Incorporated to activity 6.1 | EBRD
| 7.2 Incorporate into MEITI 2018 report | IA will reconcile the information and incorporate into the report | Mongolia EITI Report 2018 |  | Jul-Nov 2019 | 0 | WB
[5 empty] | thousand MNT | 26230.6 | WB
[5 empty] | EURO | 205000 | EBRD
Abbreviations
WB - World Bank
EBRD - European Bank for Reconstruction and Development
EITIIS - EITI International Secretariat
EITIMS - EITI Mongolia Secretariat
EITINC - EITI National Council
EITIWG - EITI Working Group
CGNC - Corporate Governance National Council
IAAC - Independent Agency Against Corruption
MoMHI - Ministry of Mining and Heavy Industry
OGP - Open Government Partnership
MNAO - Mongolian National Audit Office
OSF - Open Society Forum
PWYP - Publish What You Pay Coalition
LPRH - Legislation and Policy Research Hub

## EBRD funded
Roadmap Activity # | Activities | Partners | Timebound | Current Estimated Budget | Budget (Version 2) | Comment
1.2 | Organize Round Table meeting for Parliamentarians and Government organizations | EITIIS | Mar-Apr, 2018 | 30,000 euro | 20,000 euro | MSG members concerned who will participate, we need to invite right persons
2.3 | Draft the BO amendments to the related laws, submit the draft law | MoMHI, EITIIS, Consultancy Firm | Mar-Apr, 2018 | 50,000 euro | 50,000 euro
5.1 | Training and consultation workshop for executives and senior legal officers of companies /25 people, 3 series/ | EITIIS | May 2018 | 15,000 euro | 15,000 euro | Companies more likely to know about the benefit of BO disclosure
5.2 | Training for civil society and NGOs /15 people, 3 series/ | EITIIS | Mar-May 2018 | 40,000 euro | 20,000 euro | Separate CSO budget from the Journalists training; Also PWYP coalition expressed their interest to assure current BO information disclosed by the EITI 2013-2016 report by this type of funding
5.3 | Establish investigative journalists network and train them /10 journalists, 3 series/ | EITIIS | Mar-Dec 2017 |  | 30,000 euro | 1) Study tour and investigate some PEPs information of Mongolia and assure the current database of EITI BO 2) And produce quarterly articles/TV products/infographics though their channels | This way might be more constructive
6.1 | Synchronize the registration system of government agencies which register and maintain BO information and improve information sharing within those GOs | IAAC, CGNC, EITIWG, Consultancy Firm | Jan-Jul 2018 | 70,000 euro | 70,000 euro
6.2 | Organize training for GO's related with BO registration process |  | Aug-Oct 2018
7.1 | Link to other e-Reporting system and disclose the BO information into public | IAAC, CGNC, EITI, Media organizations | Jan-Jul 2019
6.5 | Pilot assuring process of information gathered | CSOs, IAAC, MNAO | Mar-Jun 2018 | Incorporated CSO training 5.2 budget
|  |  | Total | 205,000 euro | 205,000 euro