## UK EITI 2021 Workplan
UK EITI 2021 Workplan
No. | Activities | Timeline | Expected Output | Expected Outcome | Responsible Entity | Cost 2019-20 | Cost 2020-21 | Cost 2021-22 | RAG rating | Progress update
1. Uphold the principles set out in the 2019 EITI Standard and implement them in a way suitable for the UK context.
1.01 | Complete second validation under the EITI Standard and achieve 'satisfactory progress' | Nov-2020 onwards | Ensure that all corrective actions are addressed, progress is well documented and that the MSG is equipped to respond to any queries raised during the validation process. Engage with EITI International Secretariat and EITI Board to explain UK implementation and ensure satisfactory result. | Satisfactory progress in the UK's revalidation. | Compliance Subgroup, MSG |  |  |  |  | Work continuing to ensure that all the corrective actions are addressed. Still some work required on appointment of local representative for CSN. Secretariat and Justyna Herbut the CSN coordinator are working closely to identify suitable candidates. Also work still required on contracts and licences. Secretariat working closely with the Devolved Administrations and government agencies to satisfy this requirement. Assist in the preparation of the validation starting on 1st July, including drafting and approving the text of the three pre-validation templates covering stakeholder engagement, outcomes and impact and transparency and take part in the initial copnsultation process.
1.02 | Complete annual progress report/annual review of outcomes and impact of EITI implementation. This should now include documenting the efforts to improve gender equality and social inclusion. MSG to agree on the method for doing this. | 2021-12-01 | Written assessment of the impact of EITI implementation in 2021, the lessons learned from the past year and the extent to which EITI has met its objectives. | MSG, its constituencies and the wider public are more aware of the impact of EITI implementation in the UK. MSG can make informed decisions to increase the impact of EITI in the UK and ensure that EITI implementation is beneficial to the UK. | UK MSG & UK EITI Secretariat |  |  |  |  | Initial planning being undertaken by the Secretariat, with further discussions at the MSG on 2nd September 2021.
1.03 | Hold UK MSG every two months, with good representation from all constituencies. | 2021-12-01 | MSG meetings every 2 months with well-considered agendas and papers to ensure speedy and effective implementation of EITI. | Increased dialogue between government, industry and civil society and momentum maintained for UK EITI implementation. | UK MSG, & UK EITI Secretariat |  |  |  |  | Ongoing. Meetings held on 14th January 2021, 16th March, 12th May, 17th June and 21st July 2021. Next meeting to take place on 2nd September 2021. Further meeting on 25th November 2021.
1.04 | Civil Society Network and Secretariat to work together to ensure that remaining civil society seats are filled, including representatives from local communities. | 2021-03-01 | New civil society members of MSG, including representatives from local communities affected by the extractive industries. | Civil society is fully engaged with EITI process, with representatives from diverse parts of civil society, so that a wide range of views are brought to the MSG. | UK EITI Secretariat/Civil Society |  |  |  |  | Secretariat and Justyna Herbut the CSN coordinator are working closely to identify suitable candidates. Also asked Pat Foster to look for possible candidates in the South West region and MSG members also asked to consider possible candidates.
1.05 | MSG to monitor diversity of MSG representatives, including gender. | Ongoing | MSG to ensure that diversity issues, including gender parity, are taken into account in their nominations process in different constituencies, as set out in the Terms of Reference. | Greater gender diversity in the MSG and greater awareness in the MSG and wider sector of the need for gender parity. | UK MSG/UK EITI Secretariat |  |  |  |  | Ongoing. Any new appointments will be take into account gender and diversity considerations.
2. Promote transparent and accessible disclosure systems and good governance in the extractives sector. Enhance accountability on revenues from the UK’s extractives industries.
2.01 | Ensure that the new EITI website continues to present information on the extractive industries in a transparent and accessible way. | Ongoing | Review of website content every six months by Communications Subgroup to ensure that interactive, visually appealing content about the UK extractive industries is available online and in a timely manner | Increased understanding of the extractive industries in the UK, greater public debate and increased interest in UK EITI. | Comms Subgroup, Sectoral Subgroup UK EITI Secretariat |  |  |  |  | Ongoing. The UK EITI website is updated with new data when it becomes available. An accessibility audit has also taken place to ensure that the website adheres to accessibility guidelines for websites.
2.02 | Mainstreaming Subgroup to ensure that EITI requirements are met by systematic disclosure where MSG deems appropriate. | 2021-12-01 | Mainstreaming Subgroup to continue to oversee the implementation of recommendations from the Mainstreaming Feasibility Study, build on work from 2020. Ensure that EITI website signposts external data sources where available. MSG to consider implementing an alternative approach to the reconciliation process. | UK disclosure systems strengthened. The UK makes information required by the EITI Standard available through reporting systems and transparency becomes an integral and routine feature for the UK. UK EITI collates information and publishes any data that is not systematically disclosed. UK satisfies the requirements of 2019 EITI Standard. | Mainstreaming subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | The mainstreaming subgroup have implemented the majority of recommendations of the feasibility study. There is still some work to do regarding the mainstreaming of tax data. A paper on the mainstreaming of tax data was circulated to the MSG on 18th June 2021. The paper recommend: • To continue with the reconciliation exercise and subsequent publication of the report. The process for 2020 should be finalised and published in July 21, so a significant improvement in timeliness from previous years. • To continue to provide information on EITI web pages with links to other resources where further information can be found to inform public debate. A lot of this has been achieved already, but we must continue to look for opportunities e.g. payments to government regulations. • To continue look at mainstreaming solutions for all the revenue streams – in particular where historic reconciliation exercises have shown little adjustment/intervention required – these would be ideal candidates for future mainstreaming whilst removing the need for reconciliation. It does not need to be a one size fits all solution. The paper and way forward were approved by the MSG on 25th June 2021.
2.03 | Ensure that 2020 payments and sectoral data is published in timely fashion and in an accessible format. | 2021-10-01 | Payments data covering 2020 is published no later than October 2021 and earlier if possible, either in the format of a reconciliation and state of the industry report, or an alternative form, depending on the MSG's decisions on mainstreaming. | Enhanced accountability to the UK public on the revenues from the UK’s extractives industries. | Reconciliation Subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | The 2020 process started on 1st April 2021. The deadline for completion is 30th April 2021. The final figures (now called Payments Report) were published on the UK EITI website on 27th July 2021.
2.04 | Review and agree the scope and methodology for the 2020 payments data/reconciliation process, including on gender, contract transparency, environmental reporting and project-level reporting. | Mar/Apr 2021 | Meeting of reconciliation subgroup to discuss updates for guidance and templates, following MSG decisions on mainstreaming and scope for 2020 data. | An agreed methodology and approach for UK EITI reporting. Any proposals to exclude certain revenue streams are agreed by the MSG. | Reconciliation Subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | Several meetings of the Reconciliation subgroup to discuss the methodology, timetable and update of the guidance and templates took place. The MSG approved the plans via email on 18th February 2021.
2.05 | Independent administrator to continue to collect information from government and companies for reconciliation, subject to MSG decision on approach to reconciliation process. | Oct/Nov 2021 | Complete reconciliation of payments for companies making payments over materiality threshold of £86,000, unless MSG agree alternative approach to reconciliation process. Independent Administrator presents data in an accessible manner in 2020 report and/or on UK EITI website. MSG to review after the exercise if the reconciliation effort is still needed, and/or or a more light touch method could be used as part of mainstreaming efforts. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator | 125000 | 125000 | 125000 |  | BDO issued templates and guidance to companies for the 2020 reconciliation process on 30th March 2021.
2.06 | Agree scope and content of Independent Administrator contract, to begin June 2022. | From September 2021 | Current contract will expire on 15th June 2022. MSG to consider scope for new contract and ensure that new contract is in place in time for the reconciliation of 2021 payments. | Independent Administrator contract agreed by MSG and new contract in place before June 2022. | [5 empty] | In June 2021 the original contract was revised to accommodate a new role that includes delivery of the key elements of UK EITI communications strategy and act as secretariat for the MSG’s Communications and Sectoral subgroups.
2.07 | MSG to work with government bodies and agencies to ensure that all requirements on licence and contract transparency are met, including the requirement to disclose all contracts entered into, signed or amended from 1 January 2021. | 2021-12-01 | - Clear explanation on government policy for the disclosure of contracts and licences by different government bodies and agencies on the EITI website. - Summary of MSG's plan for ensuring compliance with the requirement on the website. - Full text of contracts and licences in scope of EITI reporting disclosed by the relevant government body or agency. All relevant information on in-scope licences and contracts disclosed, in line with EITI Standard. - Progress towards this goal is captured in contract tracker, overseen by the Compliance Subgroup. | Greater clarity on government policy and MSG's action plan on licence disclosure. All new or amended contracts from 1st January 2021 are disclosed in a way the MSG deems consistent with the requirements of the 2019 EITI Standard. Greater contract transparency in the UK extractive sector. | [5 empty] | Ongoing. The Secretariat continues to meet regularly with all licensing bodies across the UK to progress all contract and licence transparency requirements under the 2019 EITI Standard. Progress has been made, however complication have arisen around commercial sensitivities/confidentiality clauses in contracts which have impeded progress.
2.08 | MSG to consider the role of EITI in the energy transition and to consider if any further environmental payments could be disclosed, building on existing environmental payment data. | 2021-12-01 | Robust MSG discussion on the energy transition. Energy transition page on UK EITI website is maintained, with links to relevant external resources. Possible inclusion of additional payments stream in reconciliation process or additional information on sectoral pages of website. | UK EITI contributes to public debate on the energy transition. | Compliance Subgroup, Sectoral Subgroup UK EITI Secretariat and MSG |  |  |  |  | Initial discussions on energy transition took place at the MSG meeting in January 2021, it was agreed that the first action should be to map current activity in the UK. The Secretariat have also been in contact with the BEIS team working on the Task Force for Climate-related Disclosures (TCFD) and they provided an overview of their work at the March MSG. A section on energy transition has been added to the UK EITI website. The Secretariat completed an energy transition mapping exercise in May 2021 and continue to engage with EITI and other HMG colleagues on plans to use EITI data in UK Government policy and EITI's plans for a COP 26 side event. The MSG heard from Carbon Tracker and their Fossil Fuel Registry in July 2021. A further discussion around energy transition is planned for the November 2021 MSG meeting.
3. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources.
3.01 | Undertaken outreach activities to spread awareness and facilitate dialogue about EITI and the UK extractive industries. | Ongoing | Communications Subgroup to consider how outreach can continue within limits of COVID-19 restrictions and make recommendations for MSG to take forward, including organising one-off events, participation at key industry and international EITI events, articles in trade publications, quarterly newsletters and better use of social media. | Greater awareness and understanding of EITI and its importance to the transparency agenda. Increased industry and public awareness of the work of the UK EITI MSG. | Comms subgroup, UK EITI Secretariat. |  |  |  |  | The Comms subgroup have discussed possible events that the MSG can use to promote UK EITI, need to decide what is possible in current pandemic climate. An article on UK EITI was published in the Mineral Products Today magazine in July 2021. A Comms expert took over as chair of the Comms sub group in June 2021 and is reviewing further outreach and communications opportunities.
3.02 | Ensure EITI website is regularly updated and continues to present information in an interactive and accessible way. | Ongoing | Reviews of current website every six months, resulting in an accessible and up-to-date UK EITI website with interactive data on the extractive industries and links to other relevant data sources. Website includes up-to-date information about EITI and the work of the MSG with relevant sections covering both industry and civil society. | The UK EITI website is used by the industry and the public to source data for the extractive industries in the UK, thus enriching public debate. The website aids systematic disclosure/mainstreaming, with links to relevant data sources and further information on the sector. | Comms subgroup, UK EITI Secretariat. | 47000 | 10000 |  |  | The UK EITI website is updated with new data when it becomes available. An accessibility audit has also taken place to ensure that the website adheres to accessibility guidelines for websites. Further use of the website is also being discussed by the Communications sub-group.
3.03 | MSG members to promote and stimulate interest in EITI within their industry. Use MSG member networks to promote EITI report. | 2021-12-01 | MSG members to use/reference EITI in their own publications/websites, events and consultation responses. Dissemination of the report to a wider audience via events, websites and social media. | Increased understanding of EITI within industry and its importance to the transparency agenda. Report is used as a tool to improve debate on extractive industry issues. | Communications subgroup and all MSG members |  |  |  |  | The UK EITI Payments report 2020 was circulated to all MSG members with a request to circulate further via social media and via their networks.
3.04 | Ensure that the EITI Champion supports efforts on EITI implementation and is kept up-to-date on progress. | Ongoing | Submissions to EITI Champion informing them of progress. EITI Champion involvement in outreach activities and launch of report. | Greater awareness of EITI and continued Government support for EITI implementation. | UK EITI Secretariat |  |  |  |  | In March 2021 Lord Callanan wrote to all Developed Administrations and relevant government agencies to encourage them to comply with the new requirement from the 2019 EITI Standard to disclose the full text of any contracts signed, amended or entered into from 1st January 2021.
4. Contribute to international efforts to further transparent and accessible disclosure systems, common global reporting standards and good governance in the extractives sector.
4.01 | Participate in EITI calls with other implementing countries to share experiences of EITI implementation. | Ongoing | Share EITI experience with other countries via webinars and participation in conferences organised by EITI International Secretariat. | Other implementing countries or countries considering implementation learn from UK experience. The UK learns from other implementing countries to ensure more effective implementation in the UK. | UK EITI Secretariat |  |  |  |  | Ongoing. The Secretariat hold regular meetings with colleagues from the Dutch and German Secretariat's. Consideration being given to organising a meeting between MSGs to exchange experiences on a number of areas including: validation, mainstreaming, the impact of EITI and energy transition.
4.02 | Secretariat and MSG members to attend events organised by the International Secretariat to share UK experience and build connections with other implementing countries | Ongoing | Share EITI experience with other countries via webinars and participation in conferences organised by EITI International Secretariat. | Greater connections between UK EITI and other implementing countries to enable better knowledge sharing and more effective implementation. UK more aware of latest developments in EITI Standard and examples of best practice. | UK EITI Secretariat, MSG members | 5000 | 5000 | 5000 |  | The Secretariat have attended events (virtually) organised by the EITI International Secretariat covering: Looking ahead – a snapshot of innovations in resource taxation, cost transparency and revenue forecasting. Evolving expectations: How state-owned extractive companies are tackling transparency Also part-taking in conversation with EITI on energy transition - COP26 side event and use of EITI data to support policy work in the UK.
4.03 | Participate in regular calls with the EITI International Secretariat to share experiences of UK implementation in order to inform the development of the EITI Standard. | Ongoing | Share UK experience with International Secretariat, clearly communicating UK priorities for the development of the Standard. | Development of Standard informed by UK implementation experience and expertise. | UK EITI Secretariat |  |  |  |  | Ongoing. The International Secretariat have regularly attended MSG meetings and have also participated in a number of subgroup meetings. The UK Secretariat have been in regular contact with the EITI International Secretariat to discuss energy transition, contract and licence transparency and the UK's 2021 validation against the 2019 EITI Standard.
RAG rating code
Complete
On track for delivery by agreed timeline
Medium risk not on track for delivery by agreed timeline
High risk not on track for deliver by agreed timeline

## Raising public awareness (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
2. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources. | Precondition - Functions legislation to allow HMRC to engage in EITI. | 1. Lack of awareness on the extractive industries in the UK. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.1 Establish a Validation subgroup to take forward the recommendations of the validation report and look at requirements to gain full compliance. | Subgroup to make recommendations for MSG to action and take forward. | UK EITI addressed issues that validation team highlighted and UK applies again to become a fully compliant country. | UK MSG & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  |  | 1.2 Hold post-validation outreach event to provide stakeholders with an update on progress & restate UK's commitment to EITI. Possible Ministerial attendance. | Event aimed at communicating with a wider audience. | Increase awareness and support for UK implementation of EITI in the UK. | UK MSG & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.3 Hold or participate in events to raise awareness of UK EITI. Possible Ministerial/UK EITI MSG attendance. | Events aimed at raising awareness of EITI and its importance to industry and the transparency agenda. | Industry awareness of UK EITI and the work of the MSG increased. | UK MSG & UK EITI Secretariat. | 2020-03-01 |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.4 Establish an independent UK EITI website. | An independent UK EITI website with links to the relevant and up to date data. Approved by the Government Digital Service (GDS). | The UK EITI website will be the website used by the sector to source data for the industry. UK EITI moves towards systematic disclosure. | UK MSG & UK EITI Secretariat. | 2019-12-01 | 30000 |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Draft a tender for contract for establishing nrw UK EITI independent website. |  |  | UK Secretariat, BEIS Procurement and Finance, UKSBS and MSG | 2019-12-01 |  |  |  |  | Pending
|  | 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.6 Use range of communication channels to ensure that all companies within scope of UK EITI are aware of the need to report. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | July/August 2019 |  |  |  |  | On-going
|  | 3. Current inconsistent production of data. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.7 Improve guidance and templates to help in-scope companies report under EITI. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible webinar event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-06-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Set up a subgroup to take forward the recommendations of the systyematic disclosure (mainstreaming) scoping study. | Scoping study by BEIS analysts in consultation with MSG members. | The UK EITI makes information required by the EITI Standard vailable through reporting systems and transparency becomes an integral and routine feature for UK EITI. | UK MSG & UK EITI Secretariat. | July/August 2019 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.9 Independent administrator to collect information from government and companies for reconciliation | Complete reconciliation of payments. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator, HMRC, Oil and Gas Authority, The Crown Estate, Crown Estate Scotland, UK MSG & UK EITI Secretariat. | July/August 2019 |  |  |  |  | Pending
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.10 Review and agree the scope and methodology for the 2018 reconciliation process. | Meeting of reconciliation subgroup to discuss updates for guidance and templates. Need to be agreed by the MSG. | An agreed methodology and approach for UK EITI reporting. Proposals to exclude certain revenue streams need to be revisited and agreed by the MSG. | UK MSG & UK EITI Secretariat. | 2020-03-01 |  |  |  |  | Ongoing

## Accessibility of information (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
3. Ensure information is readily accessible and presented to the public in a clear manner. | Precondition- All stakeholders need to be engaged on EITI and need to have a good understanding of the extractives industry on the UK - Need an informed and engaged MSG -Expertise needed on presentation of the data. | 1. Lack of awareness on the extractive industries in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.1 Ensure that both the UK EITI gov.uk and independent UK EITI website is updated in a timely manner to provide relevant information | UK EITI website updated when there are changes in MSG membership and new documents to upload. | Valuable information source for stakeholders leading to increased understanding and awareness of UK EITI. | UK EITI Secretariat | 2019-12-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.2 Use MSG members to ensure that the report content is accessible to multiple audiences | UK EITI website updated and the annual report is available in accessible format as required by the Gov.UK website. | Maximise audience of EITI report and comply with Gov.UK regulations. | UK EITI Secretariat | Nov-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.3 Ensure the report is written in plain English | Increased support and understanding amongst key stakeholder groups | Increase understanding and awareness of UK EITI and ensure messages resonate with industry, civil society and Government representatives. | Sectoral subgroup, with review by MSG | Sept-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.4 Consider and agree the presentation of EITI reports. Short reconciliation report and "State of Industry" chapter with a number of standalone background chapters. | Access to a range of data that can be manipulated | Increase understanding of the extractive industries in the UK and encourage debate. | UK MSG & UK EITI Secretariat | Sept-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.5 Publish Annual Progress report | Overview of the work of the MSG in 2018. | Increase understanding and awareness of the work of the MSG. | UK MSG & UK EITI Secretariat | 2019-07-01 |  |  |  |  | Pending
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 2.6 Independent administrator to present EITI report to the MSG to consider and endorse before publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.7 MSG to agree EITI report ahead of publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG & UK EITI Secretariat | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.8 Agree communications plan to promote the published report | Comms subgroup to draw up a communications workplan to promote UK EITI report and other activities. | Maximise audience of EITI report | Communications sub group & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.9 Publication of annual EITI report | Publish report in timely manner. | Report is used as a tool to improve debate on extractive industry issues | UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.10 Use MSG member networks to promote EITI report | Dissemination of the report to a wide audience | Report is used as a tool to improve debate on extractive industry issues | Communications sub group, UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.11 During outreach, consult stakeholders on how to present information e.g. are the new summary report and standalone chapters an improvement? | Comments received during outreach activities | A record of outreach and comments received is maintained that should be reviewed regularly | Communications sub group and UK EITI Secretariat | 2019-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 2.12 Targeted communications to specific civil society groups to raise awareness of the EITI report | Increase awareness of the EITI report | Stimulate debate on the UK extractive industries | Communications sub group and UK EITI Secretariat | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.1 Monitor the need for training activities, workshops etc. for MSG members | Various training activities | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | UK MSG & UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.2 Invite representatives from other countries to attend MSG meetings and share UK's and their experiences. | Share experiences with colleagues from overseas. | Increased understanding of options to implement EITI for UK and other countries sharing good practice. | UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.3 Use MSG membership to promote and stimulate interest in EITI within their industry. | MSG members to use/reference EITI in their own publications/websites and consultation responses | Increased understanding of EITI within industry and its importance to the transparency agenda | UK MSG | 2020-03-01 |  |  |  |  | On-going

## Support of transparency (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
4. Support the UK government’s championing of extractives transparency and open government | Precondition- The profile of EITI needs to be raised and more needs to be done to promote what the UK is doing with implementation. Reliant on all companies complying with EITI. | 1. Only budget to cover costs of report and possible launch activity around publication. 2.DFID is responsible for international influencing. 3. Lack of awareness of EITI. | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.1 Allow nominated people to attend MSG meetings | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 4.2 Participate in EITI calls with other developed countries to share experiences | Share EITI experience with other countries via webinars and conferences organised by EITI International Secretariat. | Expand understanding of options to implement EITI for UK and other countries | UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.2 Company Engagement | 4.3 Consider methods to encourage good practice by companies | Disseminate information on good practice by companies | Helping to share good practice | UK MSG & UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 4.4 Re-engage with Civil Society Network (CSN) with view to encouraging them to return to the MSG. | Work closely with CSN colleagues to agree a return date to the MSG. | The return of CSN to the MSG | UK EITI Secretariat | 2019-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.5 Review the UK EITI MSG terms of reference. | Work with BEIS legal team to review current terms of reference. | More robust and relevant terms of reference | UK MSG, UK EITI Secretariat & BEIS Legal | 2020-04-01 |  |  |  |  | Pending
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.6 Review membership of the constituencies, including lengths of service and succession planning. | Work with both industry and civil society to agree updated mechanisms for appointing new MSG members and succession planning. | Ensure that the MSG has adequate membership and is quorate with robust succession arrangements. Industry has agreed a plan and a process is now in place. | UK MSG, UK EITI Secretariat & BEIS Legal | 2020-04-01 |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.3 Lessons learned and follow up on recommendations | 4.7 Independent administrator to make recommendations for future reconciliation processes | Generate suggestions to improve reconciliations | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive. UK EITI to benefit from continuous improvement | Independent Administrator | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 4.8 Review outcome and impacts on EITI implementation | Lessons learned on UK EITI | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive and readily accessible to stakeholders and UK benefits from continuous improvement. | UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | On-going
|  |  | Requirement 2: Contracts and licenses - 2.5 Beneficial Ownership | 5.1 Monitor and consider existing and upcoming transparency initiatives in the UK EG Chapter 10 Accounting Directive, Transparency Directive and Register of Beneficial Ownership | Ensure that UK EITI is consistent with other transparency initiatives | UK EITI will reflect other reporting requirements to ensure any additional requirements are proportionate. | UK Government and extractive companies in scope | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.1 Regular meetings of the MSG | Hold MSG meetings every 2 months to ensure speedy and effective implementation | Strengthen the participative multi stakeholder process of EITI and increase confidence among stakeholders | UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.2 Assess and outline plans to address any potential capacity restraints in Government agencies, companies and civil society organisations that may be an obstacle to implementation | MSG to consider and take steps to remove capacity constraints | Ensure speedy and effective implementation | UK MSG and UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.3 Ensure that any updates to the EITI Standard in 2019 are understood and preparations are made to ensure that any new Standards are adopted. | MSG to discuss new Standard with EITI International. | The 2018 UK EITI report reflects changes to the EITI Standard for 2019. | UK MSG, UK EITI Secretariat and EITI International Sercretariat. | 2019-09-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.5 Work Plan | 6.4 Agree and maintain and current work plan, fully coasted and aligned with the reporting and validation deadlines established by the EITI Board | Up to date UK EITI work plan | Provides direction to the MSG on what areas UK implementation should focus on | UK EITI Secretariat and UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 6.5 Agree and publish annual progress report | Lessons learned on UK EITI | Continuous improvement | UK EITI Secretariat and UK MSG | 2019-07-01 |  |  |  |  | On-going

## IA Appointment (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
1. Appointment of a new Independent Administrator. | Precondition - Independent Administrator needs to be appointed by June 2019 to ensure that the guidance and templates are circulated and made available on the UK EITI website for in-scope companies. Risk - The IA is not in place in time, therefore delaying the 2018 reporting process. | The current contract ran out on 28th February 2019. | Requirement 1 - Oversight by the multi-stakeholder group. 1.4 Multi-stakeholder group. | 1.1 Evaluation panel set up to look at and score bids received from potential IA's. Interviews to take place for highest scoring bids and evaluation panel to select the new IA. | MSG to evaluate and score all tenders and select best candidate for role of IA. | IA appointed in time for the start of the 2018 process in June 2019. | UK MSG and UK EITI Secretariat. | 2019-06-01 | 126000 | 126000 | 126000 |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed